## TASKS
Burn-Up List
Week 2 Assignments | START DATE | DUE DATE | % COMPLETE | DONE | NOTES
The Week Ahead | 2016-01-09 | 2016-01-17 | 100% | 100% | Completed First
Career Module | 2016-01-09 | 2016-01-16 | 25% | 0% | Commited to finish on Saturday
GTT | 2016-01-09 | 2016-01-11 | 100% | 1 | Attended and complete
What is a Portfolio? | 2016-01-09 | 2016-01-17 | 75% | 0 | Read through, now viewing links
How Do I create an ePortfolio? | 2016-01-09 | 2016-01-16 | 50% | 0% | Reading through material
Self Evaluation:SWOT | 2016-01-09 | 2016-01-13 | 25% | 0% | Drafting stages
Anchor Points | 2016-01-09 | 2016-01-13 | 25% | 0 | Drafting stages
Call to Action- Failure to Success | 2016-01-09 | 2016-01-16 | 25% | 0 | Gathering Ideas
Mission Statement | 2016-01-09 | 2016-01-15 | 75% | 0 | Mostly Finished
Research | 2016-01-09 | 2016-01-16 | 75% | 0% | Mostly Finished
Developoment | 2016-01-09 | 2016-01-16 | 50% | 0% | Still getting the hang of this
Project & Portfolio | 2016-01-09 | 2016-01-17 | 25% | 0 | Updating as work is completed
Burn-Up List | 2016-01-09 | 2016-01-19 | 0% | 0 | Haven't begun